## Sheet1
Type of Requirement | Requirement | Priority | Completed? | Comments
3.1.1 User Interface | The application shall be a multi-page Dashboard web application of at least 2 pages. | 1 | Y |  | Key
3.1.1 User Interface | The user interface shall display a line plot of a scalar value over time. | 1 | Y |  | Priorities: | 1 (High)
3.1.1 User Interface | The user interface shall display a line plot of a start / end datetime picker. | 1 | Y |  |  | 2 (Medium)
3.1.1 User Interface | The user interface shall display a line plot of a database source picker. | 1 | Y |  |  | 3 (Low)
3.1.1 User Interface | The user interface shall have a ‘Submit’ button which fetches the data for the line plot. | 1 | Y
3.1.1 User Interface | The user interface shall have a ‘Downsampling On/Off’ toggle. | 1 | Y
3.1.1 User Interface | The user interface shall have a ‘Downsampling’ text entry form. | 1 | Y |  | Completed: | Y (Yes)
3.1.1 User Interface | The project shall be built using Plotly Dash | 1 | N | Agreed with Nick to use Streamlit instead |  | N (No)
N/A (Non-applicable
3.1.1 User Interface | The user interface may have a multidimensional class of data displayed as a geo-heatmap or spectrograph or surface plot. | 3 | N
3.1.1 User Interface | The graphs may have additional animations or orientation controls. | 3 | N
3.1.1 User Interface | The multidimensional data may be shown below the line chart. | 3 | N
3.1.1 User Interface | The user interface may compare costs using Snowflake or Data Dog. | 3 | N
3.1.1 User Interface | The application may benchmark writing data to large tables. | 3 | N | In Progress
3.1.1 User Interface | The application may benchmark the ArcticDB time-series collections. | 3 | Y
3.2.1 Database | The database source shall use either Postgres, Postgres with TimescaleDB or ClickhouseDB. | 1 | N | In Progress
3.2.1 Database |  | 1 | Y
3.2.2 Other Interface | The team shall use the ‘Issues’ page on GitHub for logging tasks and communication. | 1 | N/A
3.3.1 Docker | For local development, the databases shall be run inside Docker containers. | 1 | Y
3.3.1 Docker | There shall be one Docker container for Postgres. | 1 | Y
3.3.1 Docker | There shall be two Docker containers for ClickhouseDB, and they shall be named ‘chc’ and ‘chs’ respectively. | 1 | Y
3.3.1 Docker | Docker Compose shall be used in deployment for starting and stopping the database Docker containers. | 1 | Y
3.3.1 Docker | There may be a Docker container for Postgres and TimescaleDB. | 2 | N
3.4 Resource | The application shall be deployed using a Python ‘venv’. | 1 | Y
3.4 Resource | The application’s packages shall be installed using Python ‘pip’. | 1 | Y
3.4 Resource | The application may be deployed using AWS EC2 or DigitalOcean. | 3 | N | Can be deployed in Streamlit but needs testing
3.5 Documentation | The team may use the ‘Wiki’ page on GitHub for system documentation. | 2 | Y
3.7 Testing | Test data shall contain visible results on a 24 hour basis | 1 | Y
3.7 Testing | Test data shall contain visible results on a 1 month basis | 1 | Y
3.7 Testing | Test data shall contain visible results on a 1 year basis | 1 | Y
3.7 Testing | Test data shall contain visible results on a 100 year basis | 1 | N | To Confirm with Nick